## Sheet1
Functional Requirements					Non-Functional Requirements
Number	Name	Description			Completion Status	Person Assigned		Number	Name	Category	Description			Completion Status	Person Assigned
FR-1.0.0	Animal Management	Implement the ability for staff to view and manage the detailed information about all animals available for adoption and provide the ability for clients to view a list of and the information of all animals for adoption.			In Progress	Skyler Gubbels		NFR-1	Easy Navigability	Usability	The menu navigation system of the system must be easy to understand and intuitive to follow. It should use standard menus such as File, Edit, View, etc. As well as custom ones tailored to the program.			In Progress	Ashlee Foureyes
FR-1.1.0	Add Animal	Staff should be able to add a new animal, being able to input detailed pofile information when the animal is created. Detailed profile information includes the below in addition to the Name and ID of the animal.			In Progress	Skyler Gubbels		NFR-2	Understandability	Usability	The function performed with every mouse click must be intuitive and easy to understand for a typical inexperienced home user. A home user should only have to search the help guide out of desire to see what the system can do and not necessity.			In Progress	Ashlee Foureyes
FR-1.1.1	Physical Traits	Species (Dog/Cat) / Breed / Size / Health (vaccination status, conditions, etc) / Age / Gender / Spayed/Neutered Status / Fur Length / Hypoallergenic Status			In Progress	Skyler Gubbels		NFR-3	Multitasking	Usability	While the ACM algorithm is being run, a staff member or client should be able to do other tasks on the system. The algorithm should not lock up the program.			Not Started
FR-1.1.2	Non-Physical Traits	Easy to travel with / Good with children / Good with other animals / Level of energy / Useful for defending a home/property / Good with strangers / Good in crowds / Sleeping patterns (e.g. nocturnal) / Level of affection / Good with loud noises / Messiness / Previous home (e.g. street rescue) / Indoor or outdoor animal / Level of exercise needed			Not Started			NFR-4	Uptime Requirement	Reliability	The system may not be down for more than one (1) hour per week. This includes all updates and patches to the system which must be carried out as part of the normal operation of the system.			Not Started
FR-1.2.0	View Animal Information — Staff	Staff should be able to see a list of all animals available for adoption.			In Progress	Skyler Gubbels		NFR-5	Error Recovery	Reliability	The system must be able to cleanly recover from errors, display a message to the user who caused the error, and must not crash as a result of normal operation.			Not Started
FR-1.2.1	View Detailed Animal Information — Staff	Staff should be able to see detailed information about a selected animal.			In Progress	Skyler Gubbels		NFR-6	Data Integrity	Reliability	The system must make backup copies of the data once every hour and must store all backup copies for the previous 24 hours, plus store one backup copy per day older than 24 hours up to one month previous.			Not Started
FR-1.2.2	View Animal Information — Clients	Implement FR-1.2.0 for clients.			Not Started			NFR-7	Algorithm Matching Speed	Performance	The ACM algorithm should be able to match one hundred (100) clients with one hundred (100) animals in under one minute at least eighty-five (85) percent of the time.			Not Started
FR-1.2.3	View Detailed Animal Information — Clients	Implement FR-1.2.1 for clients.			Not Started			NFR-8	Program Launch Time	Performance	The program should take no more than ten (10) minutes to launch under normal circumstances. The program can be considered launched when a staff member or client can interact with the system.			Not Started
FR-1.3.0	Edit Animal Information	Staff should be able to edit all of a chosen animal’s information.			Not Started			NFR-9	File Save Operations	Performance	The system should be able to save and load client and animal profiles from the filesystem without locking up the rest of the program.			Not Started
FR-2.0.0	Client Management	Clients should be able to be added to the system and their information should be editable by both staff and the respective client.			Not Started			NFR-10	Availability of Support	Supportability	The cuACS system developers should provide, for two (2) years after the final delivery date of the product, support by phone, email, and in-person assistance for the system.			Not Started
FR-2.1.0	Add Clients	Staff should be able to add new clients to the system, creating their profile with basic contact information.			Not Started			NFR-11	Future Maintainability	Supportability	Following the two (2) year support window, the software should be made available to be supported for additional time by the current maintainers or by a new company or by in-house IT staff.			Not Started
FR-2.1.1	Client Information	A client’s profile should consist of: Basic contact information, the client’s personal information regarding their attributes/personality, and their matching preferences. The client will also be assigned an ID by the system which they cannot change.			Not Started			NFR-12	Scalability	Supportability	The system should be able to be scaled in the future to handle up to 10,000 clients and 10,000 animals.			Not Started
FR-2.1.2	Client Contact Information	A client’s contact information should consist of: / Full name / Full mailing address / Phone number / Email address			Not Started			NFR-13	Programming Language	Implementation	The language which must be used for the system’s implementation is C++.			Not Started
FR-2.1.3	Client Personal Information	A client’s personal information should consist of: / Whether they have children / Whether they have other pets / Whether they travel a lot / Whether they exercise a lot / Whether they go out to crowded places often / What their typical sleeping patterns are like / Whether ot not they tend to make loud noises / Whether or not they are messy			Not Started			NFR-14	GUI Framework	Implementation	The GUI of the system must be implemented using Qt.			Not Started
FR-2.1.4	Client Matching Preferences	A client should be able to look at all of the physical and non-physical attributes of the animals and select which ones they absolutely must have, which ones they would prefer to have, which ones they feel neutral about, which ones they would rather not have, and which ones they absolutely will not accept.			Not Started			NFR-15	Persistent Storage	Implementation	All persistent data must be stored in either a flat file system or using SQLite and must be loaded into the system on launch. If data is stored in a flat file system, it can either be stored in binary format or in plain text.			Not Started
FR-2.3.0	View List of Clients	Staff should be able to view a list of all clients.			Not Started			NFR-16	Data Loading	Implementation	All persistent data must be loaded into the system on launch.			Not Started
FR-2.3.1	View Detailed Client Information	Staff should be able to view the detailed information of a selected client.			Not Started			NFR-17	View Separation	Interface	Each major part of the application should be presented in its own window or tab within one window. For example, functionality for managing clients should not be in the same tab as the output results for the matching algorithm.			In Progress	Ashlee Foureyes
FR-2.4.0	Edit Client Profile — Staff	Staff should be able to edit a chosen client’s information.			Not Started			NFR-18	Graphical User Interface	Interface	The interface for the system should be a professional-looking graphical user interface. It should not be a console-based interface.			In Progress	Ashlee Foureyes
FR-2.4.1	Edit Client Profile — Clients	Clients should be able to change the information on their own profile.			Not Started			NFR-19	Pop-up Menus	Interface	Pop-up menus should be presented to the user when a significant process has been completed such as the completion of a run of the ACM algorithm.			In Progress	Ashlee Foureyes
FR-3.0.0	The ACM Algorithm	The algorithm should be able to compute the optimal match between all clients and all animals and then output the list of matches with the ability to display detailed information as to why it arrived at that result. It should take into account the best interests of all animals in the shelter rather than producing a small set of optimal matches and a large set of sub-optimal matches.			Not Started			NFR-20	Staff–Client Separability	Operations	Staff members should be the only ones who are able to access staff functions such as creating animal profiles and running the algorithm. Similarly, clients should only be allowed to edit their profiles and should not be able to perform staff functions.			Not Started
FR-3.1.0	Matching Method	The algorithm should take into account both the full profiles of the clients and the full profiles of the animals when making matches.			Not Started			NFR-21	IT Management	Operations	A shelter’s IT department should be the managers of the system. They host the system using their resources and maintain it using their staff.			Not Started
FR-3.2.0	Output List	Once the algorithm has finished running, the system should display to staff a list of matches made. Each item in this list should include the names of the client and animal matched.			Not Started			NFR-22	Single-Host Model	Operations	The system should be designed to run on a single host. There are no requirements for distributed computing.			Not Started
FR-3.3.0	Detailed Match Information	When a staff member clicks on an item in the list of matches, a detailed view should appear showing the details of why the specific match was made. It should specify the exact rules used to compute the match and give data showing how/why the match was computed.			Not Started			NFR-23	Documentation	Packaging	The system must come packaged with all necessary documentation to allow the IT deparment of the shelter to install it easily. It must also come packaged with a user help guide for staff and clients of the shelter.			Not Started
FR-3.4.0	Launching the Algorithm	A staff member should be able to launch an instance of the algorithm to compute matches.			Not Started			NFR-24	Binary File	Packaging	The system must come packaged as a binary file to be installed by the installation script. No compilation should be necessary on the part of the end-user.			Not Started
FR-4.0.0	Persistent Storage	All animal and client data should be stored in a flat file system consisting of JSON or XML formatted data files. No database software will be used.			Not Started			NFR-25	Easy Installation	Packaging	The system must come packaged with an easy installation script which will install the program by running a single command.			Not Started
				Not Started			NFR-26	Sample Profiles	Packaging	The system must come pre-packaged with 25 complete animal profiles and 20 complete client profiles as sample profiles.			Not Started
				Not Started			NFR-27	Source Code Licensing	Legal	The source code for the system may not be open-sourced as the client wishes to keep the system private from competing shelters.			Not Started
				Not Started			NFR-28	Accessibility Standards	Legal	The system should comply with the local region’s accessibility standards (e.g. Ontario’s O. Reg. 191/11: INTEGRATED ACCESSIBILITY STANDARDS)			Not Started
				Not Started			NFR-29	Privacy Law Compliance	Legal	The system should be regional privacy law compliant. It should aim to comply with the GDPR should a similar law be enacted in the client’s region. It should not store users’ personal information in an insecure way and should handle it according to the laws of the country or region in which the software is operating.			Not Started
				Not Started					Not Started
				Not Started					Not Started
				Not Started					Not Started
				Not Started					Not Started
				Not Started					Not Started
				Not Started					Not Started
				Not Started					Not Started
				Not Started
				Not Started
				Not Started
				Not Started
				Not Started
				Not Started
				Not Started